## Instructions
Project Change Log ¦ How to use this workbook
Purpose | Record each proposed change from request through assessment, decision, and follow-through.
Start | Copy the blank Change Log sheet for your project and give each request a stable ID.
Request | Capture who asked, what would change, and why. A request is not an approval.
Assessment | Describe expected scope, schedule, cost, and deliverable effects before a decision.
Decision | Record the named authority, disposition, decision date, and effective date.
Follow-through | For approved changes, update affected baselines and assign the next action.
Proportionate use | Use only the detail your project needs; keep one authoritative record.
Example | The Worked Example is fictional and illustrates the full request-to-decision sequence.
Privacy | Avoid sensitive personal or commercial detail in broadly shared copies.

## Change Log
PMHub ¦ Project Change Log
Record the request first. Assess impact before the named authority decides. Update the baseline only after approval.
Request ID | Date raised | Requester | Proposed change | Rationale | Scope impact | Schedule impact | Cost impact | Deliverable impact | Assessment owner | Decision authority | Disposition | Decision date | Effective date | Baseline updates | Follow-through owner | Next action / date | Notes / reference

## Worked Example
Fictional example ¦ Request to decision
Illustration only: replace with your own approval process.
Request ID | Date raised | Requester | Proposed change | Rationale | Scope impact | Schedule impact | Cost impact | Deliverable impact | Assessment owner | Decision authority | Disposition | Decision date | Effective date | Baseline updates | Follow-through owner | Next action / date | Notes / reference
CR-014 | 2026-10-05 12:00 | Jordan Lee | Add a mobile approval screen to the launch scope. | Field reviewers need to approve submissions away from their desks. | Adds mobile approval workflow; no change to existing desktop scope. | Requires two additional weeks for build and UAT; proposed launch moves from 16 Nov to 30 Nov. | Estimated additional vendor spend: $8,000; finance review completed. | Adds mobile approval screen and updated training material. | Morgan Patel, delivery lead | Avery Chen, project sponsor | Approved | 2026-10-12 12:00 | 2026-10-13 12:00 | Scope baseline v3; milestone plan v5; cost forecast updated 13 Oct. | Morgan Patel | Confirm revised plan with delivery team by 15 Oct. | Fictional steering decision DEC-022; assessment attached to CR-014.